## Main page
No. | Risk Type | Risk Category | Risk | Risk Code
1 | Internal Risks | I. Construction Risks | Falling to the ground during equipment transportation | BR1
|  |  | Incorrect installation of drill frame | BR2
|  |  | Insufficient insertion depth of the protective tube | BR3
|  |  | The seam of the protective tube is not dense | BR4
|  |  | The protective tube is inclined and leaking | BR5
|  |  | Unstable water head in the protection tube | BR6
|  |  | Borehole collapse | BR7
|  |  | Bore hole tilt | BR8
|  |  | Reaming or shrinking | BR9
|  |  | Hole leakage | BR10
|  |  | The rig is malfunctioning | BR11
|  |  | Collapse when clearing the hole | BR12
|  |  | The thickness of the sediment does not meet requirements | BR13
|  |  | Skeleton deformation | BR14
|  |  | The skeleton collides with the hole wall when lifting | BR15
|  |  | Unqualified welding quality | BR16
|  |  | The skeleton elevation does not meet the requirements | BR17
|  |  | Collapse during pouring | BR18
|  |  | Pipe stuck | BR19
|  |  | Piles broken | BR20
|  |  | Pile body concrete enters mud | BR21
|  |  | Leakage and deviation of reinforcement skeleton | BR22
|  |  | Airbag destruction | BR23
|  |  | Bottom compartment tilted | BR24
|  |  | Pull rope decoupling | BR25
|  |  | Inaccuracy of lowering large tonnage steel cofferdam | BR26
|  |  | Large tensile stress on the bottom | BR27
|  |  | Cooling pipe clogging | BR28
|  |  | Mixing ratio leads to excessive hydration heat | BR29
|  |  | Environment temperature is too high | BR30
|  |  | Moisturizing work is not in time | BR31
|  | II. Materials and Equipment Risks | Material Shortage | BR32
|  |  | Material Error on form, function and specification | BR33
|  |  | Delay of Material Supply | BR34
|  |  | Material Damage in Storage | BR35
|  |  | Material Scarcity | BR36
|  |  | Delay of Equipment | BR37
|  |  | Equipment Damage | BR38
|  |  | Equipment Shortage | BR39
|  |  | Less equipment Productivity | BR40
|  | III. Construction Management Risks | Lack of safety equipment for workers | BR41
|  |  | Poor site management | BR42
|  |  | Availability camp for labours | BR43
|  |  | There no regular material test for materials in the project site | BR44
|  |  | Regular inspection of the site | BR45
|  |  | No past experience in similar project | BR46
|  |  | Incomplete knowledge about equipment | BR47
|  |  | Unexpected weather condition | BR48
|  |  | Inspection for safety equipment | BR49
|  |  | Change of top management | BR50
|  |  | Heavy equipment are not maintained periodically | BR51
|  |  | Inventory storage | BR52
|  |  | Strike and theft | BR53
|  |  | Dispute between labours | BR54
|  |  | Traffic of large vehicles during construction | BR55
|  |  | Many modifications on design are made during execution | BR56
|  | IV. Design Risks | Staff do not have sufficient knowledge about the design | BR57
|  |  | Design agencies are not monitored | BR58
|  |  | Dispute between owner and design team | BR59
|  |  | Plans of design are incompatible with execution | BR60
|  |  | The designer does not follow up design and changes made on them | BR61
|  |  | Unavailability of land and right of way that restricts access to the site | BR62
|  |  | Design Changes | BR63
|  |  | Design Variation | BR64
|  |  | Error in Design by Planner | BR65
|  |  | Error in drawing/specification | BR66
|  |  | Unclear information on the scope of work at the time of job description | BR67
|  | V. Insurance Risks | Fluctuation price in materials | BR68
|  |  | The company obtain large loans | BR69
|  | VI. Contractual Risks | Non-payment of taxes | BR70
|  |  | The owner lags behind in paying the contractors | BR71
|  |  | Low level of capability of contractor | BR72
|  |  | Improper verification of contract document | BR73
|  |  | Change in project scope and change orders | BR74
|  |  | Contactor anomalies | BR75
|  | VII. Project Managament Risks | Conflict between contactor and management team | BR76
|  |  | Lack of coordination | BR77
|  |  | Delay in approval from regulatory bodies | BR78
|  |  | Dispute | BR79
|  |  | Inadequate project information (soil test and survey report) | BR80
|  |  | Error in choosing implementation method | BR81
|  |  | Strict project schedule | BR82
|  |  | Poor program scheduling | BR83
|  |  | Delay during construction process | BR84
|  |  | Many work errors require rework | BR85
|  |  | Poor surveillance and site management | BR86
|  |  | Subcontractor failure | BR87
|  |  | Unstable government policies | BR88
|  | VIII. Time Management Risks | Political instability | BR89
|  |  | Delay during construction process | BR90
|  |  | Casting and curing time is more | BR91
|  |  | Release of funds takes time | BR92
|  |  | Long distance between procurement and project site | BR93
|  |  | Working hours of labours are enough | BR94
|  |  | Long distance between batching plant and site | BR95
|  | IX. Human Resourses | Less professional | BR96
|  |  | Less labor | BR97
|  |  | Low labor ability | BR98
|  |  | Low labor productivity | BR99
2 | External Risks | X. Environmental Risks | Earthquake | BR100
|  |  | Landslide | BR101
|  |  | Bad weather | BR102
|  |  | Late permissions | BR103
|  |  | A less secure project development environment | BR104
|  |  | Disagreement interests with citizens | BR105
|  |  | Unstable government policy | BR106
|  |  | Excessive government approval procedures | BR107
|  | XI. Economic Risks | Inexperience when pricing tenders | BR108
|  |  | Unrealistic cost estimate and schedules | BR109
|  |  | The contractors does not pay workers’ wages in due time | BR110
|  |  | Low credibility of shareholders and lenders | BR111
|  |  | Inflation | BR112
|  |  | Financial Failure of the Contractor | BR113
|  |  | Poor Estimation of Unexpected Cost | BR114
|  |  | Late Payment | BR115
|  |  | Loss due to fluctuation of interest rate | BR116

## Summary RBS
No. | Risk Type | Risk Category | Risk Description | Risk Code
1 | Internal Risks | I. Construction Risks | Falling to the ground during equipment transportation | BR1
|  |  | Incorrect installation of drill frame | BR2
|  |  | ….... | …
|  |  | ….... | …
|  | II. Materials and Equipment risks | Material Shortage | BR32
|  |  | Material Error on form, function and specification | BR33
|  | ….. | ….... | …
|  | ….. | ….... | …
2 | External Risks | X. Environmental Risks | Earthquake | BR100
|  |  | Landslide | BR101
|  |  | Bad weather | BR102
|  |  | ….... | …
|  |  | ….... | …
|  | XI. Economic Risks | Inexperience when pricing tenders | BR108
|  |  | Unrealistic cost estimate and schedules | BR109
|  |  | The contractors does not pay workers’ wages in due time | BR110
|  |  | ….... | …
|  |  | ….... | …
|  |  | Loss due to fluctuation of interest rate | BR116